## Schema Conformance Plan
Schema Conformance Tool — Sprint Plan
E2E Batch Automation Test Strategy ¦ 6 sprints, starting October 2026 ¦ DDL Queries vs MDR first, Data Model vs MDR second ¦ 2-week sprints throughout, incl. Sprint 0
Theme | Task | Team | Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6
|  |  | Oct 1 – Oct 14 | Oct 15 – Oct 28 | Oct 29 – Nov 11 | Nov 12 – Nov 25 | Nov 26 – Dec 9 | Dec 10 – Dec 23 | Dec 24 – Jan 6
Pre-requisites & Design | Set up a centralized repository for the Schema Conformance tool (Need a CI Name - Ronald proposed to use MSP NBIF CI but yet to be confirmed) | CCC team | ●
| The Architects should obtain approval from Architecture Board - Tribe CA to implement the framework with it's strategy and design architecture proposed | Architecture Board / Architects
| Provision a new Service Principal (SPN) for the Azure DevOps pipeline | MSP team | ●
| Grant SPN read-only access to ADLS storage containers (table-creation / CADDI SQL scripts) — needed first, for DDL Queries vs MDR | MSP team | ●
| Grant read-only access to Power Designer data models — needed later, for Data Model vs MDR | Data Factory squad DA's | ●
| Collect the latest MDR mapping sheets for all in-scope portfolios - FI | Data Factory squad BA's | ●
| Check if other data factory squads use similar kind of MDR mapping sheets or MDR itself? | Data Factory squad BA's | ●
| Finalize comparison engine requirements — normalise, match tables, match columns, compare datatypes, nullable, primary key etc. | Centralized team | ●
| Define Schema Comparison Report structure (Summary, Missing_Tables_*, Missing_Columns_*, Datatype_Mismatches, Datatype_Matches) | Centralized team | ●
DDL Queries vs MDR — Comparison Engine | Parse DDL queries .sql files for Pre-staging, Staging and Input Database tables Layer | Centralized team |  | ●
| Build table / column matching logic — DDL tables vs MDR baseline, both directions | Centralized team |  | ●
| Build the Schema Comparison Report module (.xlsx, all tabs) Implement resolution workflow (DA fixes PR / BA updates MDR / accepted deviation) | Centralized team |  | ●
| Integrate the DDL vs MDR check + reporting into the Azure DevOps PR pipeline | Centralized team |  |  | ●
| Run pilot on 1–2 portfolios (FI, SOV etc.); validate Summary counts reconcile to detail tabs | Portfolio teams |  |  | ●
Data Model vs MDR — Extraction & Comparison | Automate data model extraction from Collibra via Power Designer - Built by Evgeniy as Python script | Centralized team |  |  |  | ●
| Parse data model csv files for Pre-staging, Staging and Input Database tables Layer and compare with MDR | Centralized team |  |  |  | ●
| Wire Data Model vs MDR comparison output into the existing shared reporting module — no separate report build | Centralized team
Data Model vs MDR — Integration & Testing | Integrate the Data Model vs MDR check into the Azure DevOps PR pipeline | Centralized team |  |  |  |  | ●
| Handover to Portfolio Data Factory Squad - SL&I Portfolio teams to run pilot on 1–2 portfolios for Data Model vs MDR | SL& I Portfolio team |  |  |  |  | ●
Rollout & Stabilization | Roll out both DDL vs MDR and Data Model vs MDR checks to all remaining portfolios | Centralized team | [5 empty] | ●
| Triage and fix defects found during the pilots | Centralized team | [5 empty] | ●
| Document the runbook for DA / BA usage of the tool | Centralized team | [5 empty] | ●
| Handover and training for portfolio teams (DA / BA) | All Portfolio teams | [5 empty] | ●

## Synthetic Test Data Creation
Synthetic Test Data Creation Tool — Sprint Plan
E2E Batch Automation Test Strategy ¦ 6 sprints, starting October 2026 ¦ DDL Queries vs MDR first, Data Model vs MDR second ¦ 2-week sprints throughout, incl. Sprint 0
Theme | Task | Team | Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6
|  |  | Oct 1 – Oct 14 | Oct 15 – Oct 28 | Oct 29 – Nov 11 | Nov 12 – Nov 25 | Nov 26 – Dec 9 | Dec 10 – Dec 23 | Dec 24 – Jan 6
Pre-requisites & Design | Export DDL SQL Schema for SL&I portfolios (FI, SOV and PF) from Parallel Prod database using SSMS tool | Data Factory squad's | ●
| Get latest MDR's of all models to obtain domain values for pre-staging / staging table attributes | Data Factory squad BA's
| Decision on which layer of data model test data needs to be created - - Pre-Staging - Staging - Model Input database | Data Factory squad's | ●
| Tool should be generic to accept any schema or attributes and be able to generate meaningful synthetic test data | MSP team | ●
| Responsibility to run and maintain the test data creation tool to be discussed and finalized | Data Factory squad DA's | ●
| The Architects should obtain approval from Architecture Board - Tribe CA to implement the test data creation tool | Architecure Board - Tribe CA | ●
Development of Python / PySpark Scripts | Parse DDL queries .sql files for Pre-staging, Staging and Input Database tables Layer | Centralized team |  | ●
| Build table / column, Primary Key-Foreign Key relationship and other constraints as given in the schema SQL queries and data model extract provided by Evgeniy | Centralized team |  | ●
| Extract domain values for all attributes and store in a single config file to be used during synthetic data creation | Centralized team |  | ●
| Code the script to read schema, PK-FK relationships and generate synthetic test data | Centralized team |  | ●
Synthetic Data Generation and Verification Vs MDR/Schema | Run pilot on 1–2 portfolios (FI, SOV etc.); validate the data generated against the schema and primary-foreign key constraints to ensure data integrity | Centralized team |  |  | ●
| Correct the logic, domain values as per the expectations and iterate through to get peoperly connected test data | Centralized team |  |  | ●
Batch run initiation with generated data | Import generated data in TEST environment for SL&I portfolio db's | Data Factory Squad DE's |  |  |  | ●
| Trigger batch run for 1 portfolio and analyze the outcome, report any issues with calculations to CAS team and ask feedback | Data Factory Squad DE's
| Handover to Portfolio Data Factory Squad - SL&I Portfolio teams to run the data creation tool as per the need or frequency | Centralized team |  |  |  | ●
Rollout & Stabilization | Roll out the test data creation tool to all remaining portfolios one by one - Needs customization in scripts to make it more generic | Centralized team |  |  |  |  | ● | ● | ●
| Triage and fix defects found during the pilots | Centralized team |  |  |  |  | ● | ● | ●
| Document the runbook for DA / BA usage of the tool | Centralized team |  |  |  |  | ● | ● | ●
| Handover and training for portfolio teams (DA / BA) | All Portfolio teams |  |  |  |  | ● | ● | ●

## Data Ingestion Query validation
Data ingestion / Query Validation — Sprint Plan
E2E Batch Automation Test Strategy ¦ 6 sprints, starting October 2026 ¦Repo queries ( Step 1 and 2) validation , Pseudonimiyzed GRFD2 Data validation ¦ 2-week sprints throughout, incl. Sprint 206
Theme | Task | Team | Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6
|  |  | Oct 1 – Oct 14 | Oct 15 – Oct 28 | Oct 29 – Nov 11 | Nov 12 – Nov 25 | Nov 26 – Dec 9 | Dec 10 – Dec 23 | Dec 24 – Jan 6
Pre-requisites & Design | Set up a centralized repository for the Schema Conformance tool (Need a CI Name - Ronald proposed to use MSP NBIF CI but yet to be confirmed) | CCC team | ●
| The Architects should obtain approval from Architecture Board - Tribe CA to implement the framework with it's strategy and design architecture proposed | Architecture Board / Architects
| Provision a new Service Principal (SPN) for the Azure DevOps pipeline | MSP team | ●
| Access to centralized SQL server / Databricks | MSP team | ●
Step 1 Queries Validation | Setup pytest framwork | Centralized team | ●
| Establish SQL DB connection from pytest | Centralized team | ●
| Create Tests files in BDD format | Centralized team | ●
| Validate Query syntax, format required for CADDI | Centralized team | ●
| Validate data by executing the query and tests | Centralized team | ●
Step 2 queries validation / Business Rules validation | Create tests for view query - IFRS9/EAD/BIV | Centralized team |  | ●
| Create tests for Business Rules validation - IFRS9/EAD/BIV | Centralized team |  | ●
| Generate synthetic data for negative tests | Centralized team
Integrate the tests in Devops pipelines | Integrate tests into the Azure DevOps PR pipeline | Centralized team |  |  | ●
| Handover to Portfolio Data Factory Squad - Corporate | Corporate team |  |  | ●
Generate reports | Generate reports in the pipeline | Centralized team |  |  |  | ●
| Create Test plan in Devops | Centralized team |  |  |  | ●
| Update test results in Test plan( Devops) | Centralized team |  |  |  | ●
Rollout & Stabilization | Triage and fix defects found during the pilots | Centralized team |  |  |  |  | ●
| Document the runbook for DA / BA usage of the tool | Centralized team |  |  |  |  | ●
| Handover and training for portfolio teams (DA / BA) | All Portfolio teams |  |  |  |  | ●

## Batch Validation
Batch Automation — Sprint Plan
E2E Batch Automation Test Strategy ¦ 6 sprints, starting October 2026 ¦ DDL Queries vs MDR first, Data Model vs MDR second ¦ 2-week sprints throughout, incl. Sprint 0
Theme | Task | Team | Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6
|  |  | Oct 1 – Oct 14 | Oct 15 – Oct 28 | Oct 29 – Nov 11 | Nov 12 – Nov 25 | Nov 26 – Dec 9 | Dec 10 – Dec 23 | Dec 24 – Jan 6
Pre-requisites & Design | Set up a centralized repository for the Batch Automation (Need a CI Name) | Data Factory squad's | ●
| The Architects should obtain approval from Architecture Board - Tribe CA to implement the framework with it's strategy and design architecture proposed | Architecure Board - Tribe CA | ●
| Design scope should include below Azure resources - - Azure Logic App - Azure SQL DB - Azure ADF Pipeline - Azure Storage Account | Centralized team | ●
| Provision a Azure App Registration for the Azure DevOps pipeline and Automation Framework | MSP Team | ●
Development of Python / PySpark Scripts | Build a automation framework skeleton using Pytest. | Centralized team |  | ●
| Design scripts to establish connections to different Azure resources. This involves triggering a logic app, reading SQL DB's, Storage Locations and ADF pipelines. | Centralized team |  | ●
| Extract run history of each azure resources. Establish end to end traceability by mapping resournces with process flow. Validate the outcome with the expected one keeping Batch Id and Run ID as a baseline. | Centralized team |  |  | ●
| Keep test data ready for the specific portfolio at GRFD side. This may involves spliting E2E test scripts into phase manner as some of the execution are heavely time dependent. | Data Factory squad's
| Construct an end to end chain testing. | Centralized team |  |  | ●
Batch run initiation | Ensure test data is available in TEST environment. Ensure all teams are involved and informed to support from their end. (CADDI, MSP, CAS Calculator, etc) | Centralized team |  |  |  | ●
| Trigger batch run and analyze the outcome for each resournces one by one. Report any issues or feedback to concern team. | Centralized team |  |  |  | ● | ●
| Handover to MSP team to run the tests as per the need or frequency | Centralized team |  |  |  | ● | ●
Rollout & Stabilization | Roll out batch automation framework for all remaining portfolios one by one - Needs customization in scripts to make it more generic | MSP Team | [5 empty] | ● | ●
| Triage and fix defects found during the pilots | MSP Team | [5 empty] | ● | ●
| Document the runbook for DA / BA usage of the tool | MSP Team | [5 empty] | ● | ●
| Handover and training for portfolio teams (DA / BA) | MSP Team | [5 empty] | ● | ●